**Bo Dinar Time Line**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Phase** | **Status** | **Total Working days** | **Start dates** | **End dates** | **Notes** |
| **Phase 1: website and** Mobile design | Done | 6 | 21/07/2019 | 21/08/2019 |  |
| **Phase 2:** Websites UI | Working | 7 | 7/08/2019 | 25/08/2019 |  |
| **Phase 3:** Admin development | Working | 13 | 18/08/2019 | 03/09/2019 |  |
| **Phase 4:** Testing for websites | Not started | 3 | 04/09/2019 | 08/09/2019 |  |
| **Phase 5:** adding websites content | Not started | **2** | 09/09/2019 | 11/09/2019 |  |
| **Phase 7:** Mobile development | Working | **17** | 03/08/2019 | 02/09/2019 | There was Eid vacation for a week |
| **Phase 8: Testing mobile and fixing bugs** | Not started | **9** | 03/09/2019 | 15/09/2019 |  |

**Design**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Tasks** | **Status** | **Working days** | **Start dates** | **End dates** | **Notes** |
| Websitedesign | Done | 3 | 21/07/2019 | 23/07/2019 |  |
| Mobile design | Done | 3 | 18/08/2019 | 21/08/2019 |  |

**Websites UI**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Tasks** | **status** | **Working days** | **Start dates** | **End dates** | **Notes** |
| Home page | Done | 1 | 7/08/2019 | 08/08/2019 | There was Eid vacation for a week |
| Internal pages | Done | 3 | 18/08/2019 | 20/08/2019 |  |
| Responsive | Done | 2 | 20/08/2019 | 21/08/2019 |  |
| Notification- UI | Not started | 1 | 22/08/2019 | 25/08/2019 |  |

**Admin development**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Tasks** | **status** | **Working days** | **Start dates** | **End dates** | **Notes** |
| Home page- word press | Working | 3 | 18/08/2019 | 20/08/2019 |  |
| Internal pages - word press | Not started | 3 | 21/08/2019 | 25/08/2019 |  |
| Notification- word press | Not started | 2 | 25/08/2019 | 27/08/2019 |  |
| Api | Not started | 5 | 28/08/2019 | 03/09/2019 |  |

**Mobile**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Tasks** | **Status** | **Working days** | **Start dates** | **End dates** | **Notes** |
| **Mobile design coding** | Done | 5 | 03/08/2019 | 08/08/2019 | There was Eid vacation for a week |
| **Firebase settings** | Done | 3 | 18/08/2019 | 20/08/2019 |  |
| **APIs** | Not started | 7 | 21/08/2019 | 29/08/2019 |  |
| **Uploading the apps** | Not started | 2 | 01/09/2019 | 02/09/2019 |  |